**Townsview PLWEP 2019 – 2020**

**Baseline:** The results from Our School indicate that 36% of students are feeling unsafe attending our school, 24% of students are victims of moderate to severe bullying and 24% of students have moderate to high levels of anxiety and depression.

**Goal:** Our students will consistently report feeling safe at school.

**Indicators of Success**:

* Increased attendance
* Students are happy (fewer crying, fewer meltdowns)
* Fewer reports of bullying and negative behaviours
* Our School data says students feel safe

|  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | IMPLEMENTATION PLAN | | MONITORING PLAN | | | MONITORING UPDATE | |
| **Strategies/Actions** | **Responsibility** | **Timeframe** | **Evidence** | **Accountability** | **Frequency** | **Impact** | **Check Ins** |
| Provide a playground school map and have all K – 2 students ‘x’ the hot spot. | Administration | Oct. 1 – Oct. 10 | Map | Classroom Teachers | Every Term |  | € Embedded  € Continue  € Revise or revise  € Abandon  € not yet implemented |
| Administer a survey for baseline and repeat as a monitoring tool to grades 3 - 8. | Administration | October 2019 – May 2020 | OUR School Survey question about students feeling safe collected from grades 3 - 8 | Administration  Classroom Teachers | November 2019 |  | € Embedded  € Continue  € Revise or revise  € Abandon  € not yet implemented |
| Teachers/EA’s are checking in daily with all students. | Guidance Teacher | September 2019 – June 2020 | - Teachers are implementing their own strategy to monitor and track any patterns of students’ sense of safety.  - Teachers will focus PDCP lessons on bullying and safety.  - Log book in the office. | All staff | Daily |  | € Embedded  € Continue  € Revise or revise  € Abandon  € not yet implemented |
| All teachers do a book study on “Opening Minds Using Language to Change Lives’ by Peter Johnston | PL Committee | October 2019 – December 2019 | Book study is discussed at common planning meetings.  Staff is using the language that is encouraged in the book. | All staff | Once a month |  | € Embedded  € Continue  € Revise or revise  € Abandon  € not yet implemented |